## Partnership
Annex 1
1.PARTNERSHIP SUMMARY OF ACTIVITIES FOR 2002
Products/Services | Activities | Time Frame | Outcomes | End Date of Activities | Additional Remarks
1.1.Governance of Global Partnership to Stop TB | a) Meetings of Coordinating Board; b) Working Committee; c) Stop TB Partners Forum Planing | Feb & October Nov 2002 | 1.1.1 Two meetings held in Osaka Japan and in Capetown, South Africa.Key Outcomes from the Board Meeting:MOU draft between the GFATM and the Board,Establishment of a StopTB trust fund,Intensified support to High Burden countries(HBC). | Feb and Oct 2002
1.1.2 One Teleconference was organized for the CB.
1.1.3 The board working committee actively guided the secretariat throughout 2002 and 9 teleconferences were organized.
1.2.Stop TB working Group | Meetings of the Stop TB Working Groups. | On going | 1.2.1 All Stop TB Working Groups have held meeting, and Secretariat has been involved in the organization/ agenda. A draft document combining the TORs and the workplans of all the working Groups was written. | 2002-09-01 | Working groups to concretise their workplans on how to over come potential barriers to meeting the 2005 targets for case detection and cure rates.
| Cross-cutting support (Poverty reduction and TB) Information management and Databases. |  | 1.2.2 Proposals formulated on how pro poor approach in DOTS can be operationalised and presented to CB in spring 2003.
1.3.Global Plan to Stop TB | Operationalize the Global Plan to Stop TB | On going. | 1.3.1 The Global Plan to Stop TB was widely distributed to various constituences, while a brochure has been developed to support promotion of the Global Plan. | All year through
| Monitoring of Global Plan and Washington Commitment |  | 1.3.2 A paper on monitoring the financial components of the Global plan will be produced,it is to be included in the documents of "the State of the World Efforts to Stop TB in 2003"
1.4.Mobilize Resources and increase Investment in TB | Resource development plan | On going | 1.4.1 The Secretariat has catalysed the development of a WHO Guidelines for TB control in the workplace. These technical guidelines will provide the scientific evidence base for the development of more specific material for particular taget groups. | Spring'03
| Develop specific products supporting resource mobilization. | On going | 1.4.2 An online Resource Mobilization Directory is being developed by the secretariat together with an IT development firm, collaborating with the Working Groups. The Directory has been tested by potential donors from both the private and public sector by the working groups, resource mobilization specialists and independent fundraisers. | Spring'03
| Finance Issues |  | The partnership established a Stop TB Trust Fund at the World Bank to expand options available to donors wishing to make contributions to the partnership for targeted funding or to finance priority areas identified by the Co-ordinating Board.
1.5. Expansion and co-ordination of the global Partnership | Regional Stop TB meetings | On going | Three additional regional partnerships (AMRO, EURO and AFRO) were established.
| Guidelines for National partnerships National Inter-agency Committees Maintain and strengthen global partnership |  | National partnerships became operational in all but one high burden country (HBC) | All year through | Accelerate the establishment of Regional partnerships and upgrade programmes for high burden countries.

## Advocacy & Com
Annex 2
2.ADVOCACY& COMMUNICATIONS 2002 SUMMARY OF ACTIVITIES.
Products/Services | Activities | Time Frame | OUTCOMES | End Date of Activities | Additional Remarks
1.1. Strategic framework: Advocacy and Communications | Assessment and development of strategic plan for advocacy and communications | Jan-Mar 2002 | The strategic plan was completed, after three rounds of consultations involving 50 individuals. A consultation meeting in Jan'02 concluded the framework, which was presented to the Board who endorsed the direction.The Board emphasized the need to activate country related activities. | Jan-April 2002 | A comprehensive assessment of the Stop TB informations activities was completed in Nov 2002.
| Working with the Media. | 2002 | Promoted media coverage of: World Congress on TB, Washington DC; Editorial Board meetings on TB/HIV with Wash` Post and Nat`l Public Radio; 2nd meeting of TB/HIV Working group, Durban; International AIDS conference Barcelona; IUATLD Annual conference, Montreal | Jun/ Jul/Oct 2002
| Political and social mobilization | 2002 | StopTB congressional briefings in Washington DC and the UK House of Commons, London. | Jun & Dec 2002
|  |  | MOU with WHO`s Social mobilization and Training team to design, plan, monitor and evaluate COMBI projects and produce assessment tools and training guides for social mobilization. Completed planning for COMBI projects in Bangladesh, Kenya and Kerala. | 2002-12-01
|  |  | Stop TB Campaign Plan for 2003 Cricket World Cup, South Africa completed and activities started. | 2002-12-01
|  |  | Documentary film "The Return of TB" completed for distribution and broadcast in 20 selected European countries on World TB Day 2003 | 2002-12-01
| Monitoring public opinion | Jan-Mar 2002 | Regular weekly web alerts with links to TB news articles | On going
1.2. International Campaign: Countdown to 2005 Global TB Targets |  | Jan-Mar 2002
1.3. World TB day | World TB Day 2002, "Stop TB, Fight Poverty" implementation | 2002-03-01 | World TB Day was implemented successfully in over 50 country and various partners have organized events/ activities | 2002-03-01
| World TB Day Highlights 2002 | 2002-09-01 | Report completed and distributed | 2002-10-01
| World TB Day Packet 2003 | 2002-02-01 | Text materials completed | 2002-12-01
| World TB Day Screensavers (2) |  | Screen savers completed and first distributed | 2002-11-01
1.4.Public Awareness & Information Dissemination | Stop TB newsletter, Communique, Stop TB website | On going | On going, in line with the targets
| StopTB Annual Report 2001 |  | Report completed and distributed | 2002-07-01
| Participation in Professional Meetings | 2005-06-01 | Advocacy and Communication task force meetings held in Newark and New-Delhi | April/Sept 2002
EU strategy planning meeting held and Strategy Plans agreed with UK and EU
1.5.Resource Centre | StopTB Image Library |  | Completed work on all applications. Signed MOU with IUATLD for developing the library in 2003-2004 | 2002-12-01
| StopTB Display |  | New display completed and used for the World Health Assembly, Montreal Conference and Africa Regional Partners meeting | May/Oct/Dec 2002
| Reference Materials | 2002 | Production and distribution of the Stop TB Resource Library (CD-ROM) (Template for more in the series created) | 2002-11-01

## GDF
Annex 3
3.GLOBAL DRUG FACILITY(GDF)
Products/Services | Activities | Time Frame | Outcomes | End Date of Activities | Additional Remarks
3.1. An expanded applications and review mechanism for countries and NGOs | Adapt application form to include NGOs |  | Completed | 2002-07-01
| Receive application forms | Ongoing | Governments and nongovernmental organizations (NGOs) that agree to introduce, expand or maintain the diagnostic, treatment and monitoring policies of DOTS are eligible to apply for grants of TB drugs from the GDF. As well, countries and NGOs that are committed to DOTS policies and need access to standardized, high-quality TB drugs at low cost can purchase drugs through the GDF direct procurement mechanism.
GDF receives application forms from eligible countries and NGO's on an ongoing basis throughout the year.
| Review application Forms | Ongoing | The Technical Review Committee (TRC) of the GDF is a group of independent experts in TB control, drug management and TB programme management from around the world.They meet in person, via teleconference and email at least 3 times a year to review applications.
| Conduct country visits | Ongoing | Following review by the TRC, the GDF Secretariat arranges visits to applicant countries in order to: • Brief senior government officials and other stakeholders on the role of the GDF; • Explain the implications of a grant from the GDF; • Confirm fulfilment of the conditions for support from the GDF; • Clarify specifications of the drugs required; • Assess the current TB drug procurement and distribution system within the country.
| Conclude grant agreements | Ongoing | Following the country visit, the GDF secretariat prepares grant agreements for signature between WHO and the recipient country.The grant specifies the anount of drugs to be provided, the delivery date and the terms and conditions of support.
3.2.Drugs delivered to eligible countries | Establish procurement procedures/contracts | Ongoing | A significant function of the GDF is to provide grants-in-kind of essential TB drugs to countries in need.Through standardization of drug products, a bulk buying procurement system, and competitive bidding, the GDF has reduced TB drug prices by more than 30%. In December 2002, the GDF launched the direct procurement mechanism to give governments and their partner organizations who wish to buy their own drugs access to high-quality TB drugs at low cost.
3.3.A white list of prequalified manufacturers. | Establish procedures/contracts for prequalification process. | Completed | The GDF is developing a white list of manufacturers and products meeting international quality standards, through a standardised prequalification process. This process is based on document review, GMP inspection, and quality control, with prequalification on a regular basis (every 2-3 years). The white list of manufacturers and products will be published, enabling agencies and countries procuring TB drugs to identify sources of products of quality assured drugs.
| Initial screening of potential suppliers | Ongoing | SGS won a limited international competitive bid to carry out the screening of potential manufacturers, and received over 70 expressions of interest. A second invitation of Expressions of Interest (EOI) to manufacturers interested in being pre-qualified as suppliers of specific TB products through the GDF, was issued in December 2002. The GDF signed an agreement with WHO Department of Essential Drugs and Medicines to carry out a prequalification process for TB drug manufacturers that pass the initial screening by SGS, | 2002-12-01
| Physical audits | Ongoing | The process for the prequalification of manufacturers of TB products is well underway. A team of evaluators in mid-September 2002 reviewed product dossiers from manufacturers that were shortlisted. Physical site inspections of the manufacturers began in late September 2002. Sites in Kenya, India, Pakistan, Bangladesh and Malta were evaluated during the last quarter of 2002, with additional inspections planned for the New Year. The first whitelist of prequalified TB manufacturers is expected to be published early in 2003.
| Laboratory analysis | Ongoing
3.4.Monitoring mechanism | Establish procedures/contracts for monitoring | Completed | GDF support is provided in principle for a three-year period, subject to availability of resources, and satisfactory compliance with GDF conditions of support, including annual independent monitoring. All recipients of grants of first-line tuberculosis drugs from the Global TB Drug Facility agree, as a condition of support, to regular assessments of: (1) Adherence to GDF terms and conditions of support. (2) Programme management (including case detection and treatment outcome), (3) financial management and (4) drug management. (5) Estimated drugs needs for next year of GDF support. (6) Follow up on recommendations made by the TRC. The international agency or institution that normally provides technical support and monitoring of the NTP, monitors the use of the GDF drugs and assesses the above as part of their regular monitoring mission. The country submits this monitoring mission report, together with information on GDF drug arrival, customs clearance, drug registration, and the quarterly reports on case finding and treatment outcomes and annual WHO TB data collection form to the STB secretariat. This information, known as a monitoring dossier, is then sent to the desk auditors.
| Select monitoring agencies | Ongoing | The Desk Auditors for the GDF were appointed, through a competitive process in October 2002. They are currently Management Sciences for Health (MSH) and the German Leprosy Relief Organisation (GLRA).The role of the desk auditor is to review the monitoring dossier for completeness, consistency and credibility, and to determine whether the information included is sufficient to enable the GDF Technical Review Committee (TRC) to make an assessment of whether the GDF terms and conditions of support have been met. | 2002-10-01
| Desk Audit | Ongoing | 4 desk audits were carried out in October 2002
| Country visits | Completed
| Technical Agencies-skills development | Ongoing | GDF ran a training session in the Montreal IUATLD meeting for consultants and technical agencies carrying out consulting work. training in GDF country and monitoring missions.
3.5.Sustained Financing | Resource mobilization | Ongoing
3.6.Awareness and support for the GDF | Relationship management | Ongoing
| Advocacy and communications for the GDF | Ongoing | A generic advocacy kit for the GDF, including a CD ROM, posters, fact sheets, GDF Highlights, PowerPoint's, newsletter and overheads was developed in October 2001 and updated in October 2002. The GDF continues to be highlighted in each STB monthly communiqué.
At the country level, each country visit includes full briefings on the GDF, with other donors and key Government stakeholders, as well as press conferences. GDF was highlighted at the IUATLD conference in Montreal, Canada, in October 2002, via press releases and with formal presentations and sessions on how to apply to the GDF and buy drugs from the GDF. A video showcasing GDF achievements in Moldova was also released. This film has recently been accepted for showing at the 2003 French Cine Santé Film festival.
In the October 2002 edition of Canada's Globe and Mail, the GDF was praised for its success in negotiating low prices for TB drugs and upon delivery of the drugs, ensuring that treatment is carried out properly. Canada was honoured with a special medal from the IUATLD to recognise its commitment to fighting TB. The Minister of International Co-operation, Susan Whelan, who accepted the award, said that the GDF has become the cornerstone of the program and it will change the way foreign-aid dollars are spent.
GDF secretariat staff participated in several international meetings in 2002 to promote awareness about the GDF and to brief potential applicants on the procedures involved when submitting an application to the GDF. These included:MSH/STB Drug management meeting, Washington, USA, June 2002. 2nd meeting of the Global Working Group on TB/HIV Durban, South Africa, June 2002. Second TB Balkan meeting, Predeal, Romania, July 2002. 3rd DOTS Expansion Working Group Meeting, Montreal, Canada, October 2002. 33rd IUATLD World Conference on Lung Health, Montreal, Canada, October 2002
| International GDF promotion positioning papers | Ongoing | Positioning papers on 4FDCs, standardisation, procurement, drug management, patient kit justifications, and global TB market survey were written by the secretariat.
Staff salaries, training and information system