## COVER
PROPOSED STOP TB PARTNERSHIP SECRETARIAT WORKPLAN
2004-2005

## CONTENTS
CONTENTS
Page
1 | Budget Summary
2 | Budget details by area of work
Support and Innovations
| Governance | 5
| Coordination and Growth | 6
| Working Groups | 7
| Advocacy and Communication | 8
Global Drug Facility
| Application Review and Monitoring | 12
| Supply | 14
| Drug Management | 17
| General Management and Support | 19
General Management and Administration
| Resource Mobilization and Financial Management | 23
| Information Management | 24
| General Administration | 25
3 | Division of Workplan by year 2004-2005
4 | Comparative Workplans - 2002-2003 vs 2004-2005

## BUDGET SUMMARY
Area of Work | Products/Activities | P Staff | G-Staff | Staff costs | Activity cost | Planned cost | For CB Decision
1. Support and Innovations | Governance
| Coordinating Board Meeting | 25600 | 12400 | 38000 | 200000 | 238000 | 0
| Coordinating Board Working Committee and Teleconferences | 16000 | 0 | 16000 | 50000 | 66000 | 0
| Global planning and monitoring (Global Plan 2006-2010) | 89600 | 0 | 89600 | 374000 | 463600 | 463600
| Strategic internal planning | 160000 | 0 | 160000 | 400000 | 560000 | 400000
| External Relations | 96000 | 0 | 96000 | 120000 | 216000 | 0
| Sub-total for Governance | 387200 | 12400 | 399600 | 1144000 | 1543600 | 863600
Coordination and Growth
| Partners Forum | 76800 | 37200 | 114000 | 500000 | 614000 | 614000
| Partnership Directory | 32000 | 15500 | 47500 | 0 | 47500 | 0
| Partnership Coordination - International | 32000 | 31000 | 63000 | 80000 | 143000 | 0
| Partnership Coordination -Regional support | 64000 | 7750 | 71750 | 1320000 | 1391750 | 1391750
| Partnership Coordination - National support | 112000 | 3100 | 115100 | 500000 | 615100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total for Coordination and Growth | 316800 | 94550 | 411350 | 2400000 | 2811350 | 2005750
Working Groups
| All working groups will develop annual progress report, workplan and budget. All working groups will develop and annually update a research agenda | 179200 | 86800 | 266000 | 580000 | 846000 | 540000
| To ensure collaborative interactions and cross-fertilization among the six working groups | 64000 | 38750 | 102750 | 80000 | 182750 | 0
| To facilitate the creation of an enabling environment for the development of new tools for tuberculosis control | 224000 | 7750 | 231750 | 40000 | 271750 | 0
| To ensure that the work groups are focused on the most important areas in tuberculosis control and are structured optimally to enable the partnership to meet its goals | 96000 | 15500 | 111500 | 70000 | 181500 | 0
| Sub-total for Working Groups | 563200 | 148800 | 712000 | 770000 | 1482000 | 540000
Advocacy and Communication
| Management of the Task Force | 332800 | 27900 | 360700 | 310000 | 670700 | 0
| Global advocacy | 352000 | 68200 | 420200 | 1185000 | 1605200 | 860000
| National and subnational communication | 320000 | 130200 | 450200 | 1775000 | 2225200 | 1250000
| Information Products | 112000 | 13950 | 125950 | 320000 | 445950 | 0
| Sub-total for Advocacy and Communications | 1116800 | 240250 | 1357050 | 3590000 | 4947050 | 2110000
| Total for Support and Innovations | 2384000 | 496000 | 2880000 | 7904000 | 10784000 | 5519350
2. Global Drug Facility | Application Review and Monitoring (ARM) - Costings
| Demand assessment for GDF/GLC services (drugs, direct procurement and diagnostics) | 12800 | 0 | 12800 | 0 | 12800
| Demand creation for GLC services (drugs, direct procurement and diagnostics) | 51200 | 0 | 51200 | 100000 | 151200
| Application and Review Process for GDF/GLC | 505600 | 127100 | 632700 | 500000 | 1132700
| GDF/GLC monitoring review of GDF/GLC applications and review processes and documents | 636800 | 57350 | 694150 | 491000 | 1185150
| GDF phase out strategy | 12800 | 0 | 12800 | 0 | 12800
| Sub-total for ARM | 1219200 | 184450 | 1403650 | 1091000 | 2494650
Supply(SUP)
| Improved quality of 1st & 2nd line anti-TB drugs supplied globally | 25600 | 46500 | 72100 | 550000 | 622100
| Efficient procurement and quality control of 2nd line anti-TB drugs through competitive selection of Procurement & Quality Control Agents for first & second line anti-TB drugs | 108800 | 49600 | 158400 | 10000 | 168400
| Timely supply of second line anti-TB drugs (IDA) | 83200 | 4650 | 87850 | 0 | 87850
| Improved effciency and quality of supply of second line anti-TB drugs (New PA) | 102400 | 13950 | 116350 | 1648000 | 1764350
| Efficient supply of quality first line anti-TB drugs | 51200 | 6200 | 57400 | 64350000 | 64407400
| Improved delivery lead times and monitoring of supply through close coordination of supply agents for first line drugs and effective management of anti-TB drugs stockpile(s) | 198400 | 18600 | 217000 | 169000 | 386000
| Develop procurement and distribution strategy for TB diagnostics and laboratory equipment for TB and MDR-TB treatment | 12800 | 0 | 12800 | 0 | 12800
| Sub-total for SUP | 582400 | 139500 | 721900 | 66727000 | 67448900
Drug Management
| Improved national and international TB drug Manufacturing | 28800 | 4650 | 33450 | 10000 | 43450
| Update TB drug market survey report | 9600 | 1550 | 11150 | 0 | 11150
| Improve Drug Management in GDF/GLC supported countries | 28800 | 0 | 28800 | 0 | 28800
| Data base and planner of GDF / GLC monitoring missions | 9600 | 0 | 9600 | 30000 | 39600
| To develop a monitoring system for procurement and consumption of second line drugs | 16000 | 0 | 16000 | 0 | 16000
| Strategy development in collaboration with DEWG to promote in-country 1st & 2nd line TB drug management | 0 | 0 | 0 | 40000 | 40000
| Facilitate incorporation of Drug Management plans into DOTS expansion plans | 0 | 0 | 0 | 20000 | 20000
| Strategy development in collaboration with DEWG and EDM to promote use of FDCs | 9600 | 0 | 9600 | 5000 | 14600
| Sub-total for DM | 102400 | 6200 | 108600 | 105000 | 213600
General Management and Support
| GDF Public Relations (Global) | 0 | 0 |  | 354000 | 354000
| Service promotion (Grant Advocacy) | 57600 | 0 | 57600 | 120000 | 177600
| Service promotion (Direct Procurement Advocacy) | 44800 | 0 | 44800 | 24000 | 68800
| Service promotion (Product Advocacy) | 12800 | 0 | 12800 | 20000 | 32800
| Service promotion (Whitelist Advocacy) | 0 | 0 | 0 | 10000 | 10000
| Resource mobilisation | 118400 | 0 | 118400 | 0 | 118400
| Internal management | 460800 | 80600 | 541400 | 4000 | 545400
| Information management | 128000 | 37200 | 165200 | 0 | 165200
| Sub-total for GMS | 822400 | 117800 | 940200 | 532000 | 1472200
0
| TOTAL FOR GDF | 2726400 | 447950 | 3174350 | 68455000 | 71629350
0
3. General Management and Administration | Resource Mobilization and Financial Management | 496000 | 144150 | 640150 | 170000 | 810150 | 0
| Information Tools | 339200 | 34100 | 373300 | 210000 | 583300 | 0
| Office management | 262400 | 162750 | 425150 | 140000 | 565150 | 0
| TOTAL FOR GMA | 1097600 | 341000 | 1438600 | 520000 | 1958600 | 0
0
| TOTAL WORKPLAN COSTS | 6208000 | 1284950 | 7492950 | 76879000 | 84371950 | 5519350

## PAC-GOV COSTING
1. Support and Innovations
1.1 Governance (GOV) - Costings
Products | No | Activities | Responsible Officer | Components | P - staff % of Time | G - staff % of Time | No. of visits or Units | Unit Cost | Staff cost |  | Cost of Activities | Planned Costs | For CB Decision
[5 empty] | 133 | 21 |  | 320000 | P
[8 empty] | 155000 |  | G
Governance | 1.1.1 | Coordinating Board Meeting | Exec Sec and Petra | Staff time | 8 | 0 |  |  | 25600 | 0 |  | 25600
|  |  |  | Meetings | 12 | 8 | 4 | 50000 |  | 12400 | 200000 | 212400
|  | Sub-total | [6 empty] | 25600 | 12400 | 200000 | 238000
| 1.1.2 | Coordinating Board Working Committee and Teleconferences | Exec and Petra | Staff time | 4 | 4 |  |  | 12800 |  |  | 12800
|  |  |  | Meetings - Working Committee | 1 | 1 | 2 | 25000 | 3200 |  | 50000 | 53200
|  | Sub-total | [6 empty] | 16000 | 0 | 50000 | 66000
| 1.1.3 | Global planning and monitoring (Global Plan 2006-2010) | Sarah and Phil H. | Staff time | 24 | 8 |  |  | 76800 |  |  | 76800 | 76800
|  | Production of report |  | APW |  |  | 1 | 100000 |  |  | 100000 | 100000 | 100000
|  | Financial analysis |  | APW | 4 |  | 1 | 100000 | 12800 |  | 100000 | 112800 | 112800
|  | Editorial committee meetings |  | Meetings |  |  | 3 | 50000 |  |  | 150000 | 150000 | 150000
|  | Monthly coordination - teleconferences |  | Cost of teleconferences |  |  | 24 | 1000 |  |  | 24000 | 24000 | 24000
|  | Sub-total | [6 empty] | 89600 | 0 | 374000 | 463600 | 463600
| 1.1.4 | Strategic internal planning | Exec Sec and P staff | Staff time | 50 |  |  |  | 160000 |  |  | 160000
|  | Contract with Liverpool School of Medicine re TB and Poverty | Ger | APW |  |  | 1 | 400000 |  |  | 400000 | 400000 | 400000
|  | Sub-total | [6 empty] | 160000 | 0 | 400000 | 560000 | 400000
| 1.15 | External Relations | Exec Sec and all Prof staff | Staff time | 30 |  |  |  | 96000 |  |  | 96000
|  | Visit to partners |  | Duty travel |  |  | 24 | 5000 |  |  | 120000 | 120000
|  | Sub-total | [6 empty] | 96000 | 0 | 120000 | 216000
|  | TOTAL FOR GOVERNANCE | [6 empty] | 387200 | 12400 | 1144000 | 1543600 | 863600

## PAC-CnG COSTING
1. Support and Innovations (S&I)
1.2 Coordination and Growth (C&G) - Costings
Products | No | Activities | Responsible Officer | Components | P - staff % of Time | G - staff % of Time | No. of visits or Units | Unit Cost | Staff cost |  | Cost of Activities | Planned Costs | For CB Decision
[5 empty] | 99 | 61 |  | 320000 | P
[8 empty] | 155000 |  | G
Coordination and Growth | 1.1.1 | Partners Forum | Petra | Staff time | 24 | 24 |  |  | 76800 | 37200 |  | 114000 | 114000
|  | 3rd Partner's Forum |  | Meetings |  |  | 1 | 500000 |  |  | 500000 | 500000 | 500000
|  | Sub-total | [6 empty] | 76800 | 37200 | 500000 | 614000 | 614000
| 1.1.2 | Partnership Directory | Petra | Staff time | 10 | 10 |  |  | 32000 | 15500 |  | 47500
|  | Sub-total | [6 empty] | 32000 | 15500 | 0 | 47500
| 1.1.3 | Partnership Coordination - International | Exec Sec Ger | Staff time | 10 | 20 |  |  | 32000 | 31000 |  | 63000
|  | 2 travels for 4 persons for 2 years |  | Duty travel |  |  | 16 | 5000 |  |  | 80000 | 80000
|  | Sub-total | [6 empty] | 32000 | 31000 | 80000 | 143000
| 1.1.4 | Partnership Coordination -Regional support | Ger | Staff time | 20 | 5 |  |  | 64000 | 7750 |  | 71750 | 71750
|  | 3 travels for 2 persons for 2 years |  | Duty travel |  |  | 12 | 5000 |  |  | 60000 | 60000 | 60000
|  | 3 meetings - 2004 3 meetings - 2005 |  | Meetings |  |  | 6 | 50000 |  |  | 300000 | 300000 | 300000
|  | Four Regional focal points |  | STCs/STPs |  |  | 4 | 240000 |  |  | 960000 | 960000 | 960000
|  | Sub-total | [6 empty] | 64000 | 7750 | 1320000 | 1391750 | 1391750
| 1.1.5 | Partnership Coordination - National support | Ger | Staff time | 35 | 2 |  |  | 112000 | 3100 |  | 115100
|  | 10 travels for 1 persons for 2 years |  | Duty travel |  |  | 20 | 5000 |  |  | 100000 | 100000
|  | 4 meetings - 2004 4 meetings -2005 |  | Meetings |  |  | 8 | 50000 |  |  | 400000 | 400000
|  | Sub-total | [6 empty] | 112000 | 3100 | 500000 | 615100
|  | TOTAL FOR COORDINATION AND GROWTH | [6 empty] | 316800 | 94550 | 2400000 | 2811350 | 2005750

## PAC-WG COSTING
1. Support and Innovations(S&I)
1.3 Working Groups (WG) - Costings
Products | No | Activities | Responsible Officer | Components | P - staff % of Time | G - staff % of Time | No. of visits or Units | Unit Cost | Staff cost |  | Cost of Activities | Planned Costs | For CB Decision
[5 empty] | 176 |  |  | 320000 | P
[6 empty] | 101 |  | 155000 |  | G
All working groups will develop annual progress report, workplan and budget. All working groups will develop and annually update a research agenda | 1.1.1 | To provide coordination for separate annual meetings of each of the six working groups as requested | Sarah Phil H. | Staff time | 20 | 20 |  |  | 64000 | 31000 |  | 95000
|  |  |  | Meetings |  |  | 6 | 50000 |  |  | 300000 | 300000 | 300000
| 1.1.2 | Based on identified shortfalls in funding and gaps in investigative areas, seek opportunities for funding research to develop new tools for tuberculosis control | Sarah Phil H. PRA | Staff time | 8 | 30 |  |  | 25600 | 46500 |  | 72100
|  |  |  | Duty travel |  |  | 4 | 5000 |  |  | 20000 | 20000
| 1.1.3 | Assist working groups in developing biennial work plans and budgets | Sarah Phil H. PRA | Meetings | 8 | 2 |  |  | 25600 | 3100 |  | 28700
|  |  |  | Duty travel |  |  | 4 | 5000 |  |  | 20000 | 20000
| 1.1.4 | Provide coordination for 1 annual meeting and 6 teleconferences of the core groups of each of the 6 working groups | Sarah Phil H. | Staff time | 20 | 4 |  |  | 64000 | 6200 |  | 70200
|  |  |  | Meetings |  |  | 12 | 20000 |  |  | 240000 | 240000 | 240000
|  | Sub-total | [6 empty] | 179200 | 86800 | 580000 | 846000 | 540000
To ensure collaborative interactions and cross-fertilization among the six working groups | 1.2.1 | Provide coordination for an annual meeting of the chairs and secretariat focal points of all 6 working groups | Sarah Phil H. | Staff time | 10 | 20 |  |  | 32000 | 31000 |  | 63000
|  |  |  | Meetings |  |  | 2 | 30000 |  |  | 60000 | 60000
| 1.2.2 | Develop and maintain web-based communications among all working groups | Sarah IT | Staff time | 10 | 5 |  |  | 32000 | 7750 |  | 39750
|  |  |  | APW |  |  | 1 | 20000 |  |  | 20000 | 20000
|  | Sub-total | [6 empty] | 64000 | 38750 | 80000 | 182750 | 0
To facilitate the creation of an enabling environment for the development of new tools for tuberculosis control | 1.3.1 | Work with the 3 new tools working groups to identify nonscientific barriers to the development of new tools | Sarah | Staff time | 40 | 5 |  |  | 128000 | 7750 |  | 135750
| 1.3.2 |  |  | Duty travel |  |  | 4 | 5000 |  |  | 20000 | 20000
| 1.3.3 | Coordinate the development of solutions for reducing nonscientific barriers | Sarah | Staff time | 30 | 5 |  |  | 96000 |  |  | 96000
|  |  |  | Duty travel |  |  | 4 | 5000 |  |  | 20000 | 20000
|  | Sub-total | [6 empty] | 224000 | 7750 | 40000 | 271750 | 0
To ensure that the work groups are focused on the most important areas in tuberculosis control and are structured optimally to enable the partnership to meet its goals | 1.4.1 | Coordinate the activities of a task force organized by the Coordinating Board to examine the structure, roles, and responsibilities of the working groups and to develop mechanisms for creating and dissolving working groups | Sarah | Staff time | 30 | 10 |  |  | 96000 | 15500 |  | 111500
|  |  |  | Duty travel |  |  | 4 | 5000 |  |  | 20000 | 20000
|  |  |  | Meetings |  |  | 2 | 25000 |  |  | 50000 | 50000
|  | Sub-total | [6 empty] | 96000 | 15500 | 70000 | 181500 | 0
|  | TOTAL FOR WORKING GROUPS | [6 empty] | 563200 | 148800 | 770000 | 1482000 | 540000
4.?

## PAC-A&C COSTING
1. Support and Innovations (S&I)
1.4 Advocacy and Communications (A&C) - Costings
Products | No | Activities | Responsible Officer | Components | P - staff % of Time | G - staff % of Time | No. of visits or Units | Unit Cost | Staff cost |  | Cost of Activities | Planned Costs | For CB Decision
[5 empty] | 349 |  |  | 320000 | P
[6 empty] | 155 |  | 155000 |  | G
Management of the Task Force | 1.1.1 | Prepare, review and approve annual communications and advocacy plan with Task Force members, NTPs, WGs and GDF | ML | Staff time | 5 | 5 |  |  | 16000 | 7750 |  | 23750
|  | Annual meetings |  | Meetings |  |  | 2 | 40000 |  |  | 80000 | 80000
|  |  |  | Duty travels |  |  | 6 | 5000 |  |  | 30000 | 30000
| 1.1.2 | Revise key messages and activities to support reinforce branding of the partnership and support to the GPSTB in accordance with policy developments of the Coordinating Board | ML | Staff time | 2 |  |  |  | 6400 |  |  | 6400
| 1.1.3 | Coordinate core group of Task Force members to strengthen coordination of workplan activities, ensure transparency and improve reporting to constituents | ML | Staff time | 10 | 5 |  |  | 32000 | 7750 |  | 39750
|  |  |  | Meetings |  |  | 2 | 20000 |  |  | 40000 | 40000
|  |  |  | Duty travels |  |  | 4 | 5000 |  |  | 20000 | 20000
| 1.1.4 | Plan/coordinate support for strategic global initiatives | ML | Staff time | 15 | 2 |  |  | 48000 | 3100 |  | 51100
|  |  |  | Duty travels |  |  | 4 | 5000 |  |  | 20000 | 20000
| 1.1.5 | Strategic research to identify and exploit advocacy and communication opportunities | ML | Staff time | 2 | 1 |  |  | 6400 | 1550 |  | 7950
| 1.1.6 | Liaising with Working Groups | ML | Staff time | 5 |  |  |  | 16000 |  |  | 16000
| 1.1.7 | Catalyze advocacy and communications support activities by partners, and transfer A&C working methodology to WGs | ML | Staff time | 10 |  |  |  | 32000 |  |  | 32000
|  |  |  | Duty travels |  |  | 4 | 5000 |  |  | 20000 | 20000
|  |  |  | Meetings |  |  | 4 | 10000 |  |  | 40000 | 40000
| 1.1.8 | Work directly with GDF team, and catalyze support by partners, to maintain regular A&C activities to achieve strategic GDF objectives | AC Officer | Staff time | 25 |  |  |  | 80000 |  |  | 80000
| 1.1.9 | Networking to build strategic alliances, expand the number of collaborating partners to add capacity to the Advocacy and Communications Task Force, and actively engage them in workplan activities | ML | Staff time | 15 | 5 |  |  | 48000 | 7750 |  | 55750
|  |  |  | Duty travels |  |  | 4 | 5000 |  |  | 20000 | 20000
|  |  |  | Meetings |  |  | 4 | 10000 |  |  | 40000 | 40000
| 1.1.10 | Guidance and supervision of A&C staff | ML | Staff time | 15 |  |  |  | 48000 |  |  | 48000
|  | Sub-total | [6 empty] | 332800 | 27900 | 310000 | 670700 | 0
Global advocacy | 1.2.1 | Catalyze visits to HBCs by legislators and aides | ML | Staff time | 10 | 5 |  |  | 32000 | 7750 |  | 39750
|  |  |  | APWS |  |  | 6 | 50000 |  |  | 300000 | 300000 | 300000
| 1.2.2 | Coordinate meetings/briefings on TB with donor legislators and aides | ML | Staff time | 5 | 2 |  |  | 16000 | 3100 |  | 19100
|  |  |  | APWS |  |  | 8 | 5000 |  |  | 40000 | 40000
| 1.2.3 | Develop needed information to support political advocacy, ie donor 'fair share' lists, legislative calendars, key contacts | ML | Staff time | 3 |  |  |  | 9600 |  |  | 9600
| 1.2.4 | Coordination and support for press conferences and briefings, media networking to build interest in TB | AC Officer | Staff time | 15 | 5 |  |  | 48000 | 7750 |  | 55750
|  |  |  | Duty travels |  |  | 8 | 5000 |  |  | 40000 | 40000
|  |  |  | APWs |  |  | 8 | 20000 |  |  | 160000 | 160000 | 160000
| 1.2.5 | Coordinate with WHO regional offices, partners and consultants | AC Officer | Staff time | 5 | 3 |  |  | 16000 | 4650 |  | 20650
|  |  |  | Duty travels |  |  | 4 | 5000 |  |  | 20000 | 20000
| 1.2.6 | Develop and maintain media contacts list in collaboration with partners | AC Officer | Staff time | 2 | 2 |  |  | 6400 | 3100 |  | 9500
| 1.2.7 | Coordinate media support activities for WG meetings and global TB conferences | AC Officer | Staff time | 10 | 5 |  |  | 32000 | 7750 |  | 39750
|  |  |  | APWs |  |  | 6 | 10000 |  |  | 60000 | 60000
| 1.2.8 | Catalyze and coordinate organization of special events for TB, ie concerts, exhibitions, sports and celebrity events | AC Officer | Staff time | 15 | 10 |  |  | 48000 | 15500 |  | 63500
|  |  |  | APWs |  |  | 6 | 50000 |  |  | 300000 | 300000 | 300000
| 1.2.9 | Target global and regional tie-in events with TB advocacy activities, ie Int'l AIDS conference, WEF summits | AC Officer | Staff time | 5 | 2 |  |  | 16000 | 3100 |  | 19100
|  |  |  | APWs |  |  | 6 | 20000 |  |  | 120000 | 120000
| 1.2.10 | Coordinate ongoing campaign linking media advocacy and events in a cohesive strategy with consistent messages to support GPSTB | AC Officer | Staff time | 5 |  |  |  | 16000 |  |  | 16000
|  |  |  | APWs |  |  | 2 | 50000 |  |  | 100000 | 100000 | 100000
| 1.2.11 | Develop WTBD theme and messages consistent with campaign; provide guidance to partners in preparing activities; work with partners and WHO regional offices to organize WTBD highlight events | AC Officer | Staff time | 10 |  |  |  | 32000 |  |  | 32000
| 1.2.12 | Develop and coordinate implementation of A&C strategy for Partners' Forum that reinforces campaign messages and exploits media opportunities | ML | Staff time | 10 | 5 |  |  | 32000 | 7750 |  | 39750
|  |  |  | Duty travels |  |  | 1 | 5000 |  |  | 5000 | 5000
| 1.2.13 | Coordinate with Resource Mobilization Officer to link A&C strategy, messages and activities with RM objectives | AC Officer PRA | Staff time | 5 |  |  |  | 16000 |  |  | 16000
| 1.2.14 | In collaboration with partners, develop indicators for advocacy and media activities and monitoring tools to assess impact | ML | Staff time | 10 | 5 |  |  | 32000 | 7750 |  | 39750
|  |  |  | APWs |  |  | 2 | 20000 |  |  | 40000 | 40000
|  | Sub-total | [6 empty] | 352000 | 68200 | 1185000 | 1605200 | 860000
National and subnational communication | 1.3.1 | Develop indicators, guidelines and TORs to use in reviewing communication components of TB programs during Country Technical Review Missions (CTRM) | SS | Staff time | 4 | 4 |  |  | 12800 | 6200 |  | 19000
|  |  |  | Duty travel |  |  | 2 | 5000 |  |  | 10000 | 10000
|  |  |  | APW |  |  | 1 | 10000 |  |  | 10000 | 10000
| 1.3.2 | Develop and pretest communication and social mobilisation (CSM) indicators for adoption by DEWG | SS | Staff time | 8 | 6 |  |  | 25600 | 9300 |  | 34900
|  |  |  | APW |  |  | 1 | 20000 |  |  | 20000 | 20000
|  |  |  | Duty travel |  |  | 4 | 5000 |  |  | 20000 | 20000
| 1.3.3 | Incorporation of CSM indicators in NTP annual reports | SS | Staff time | 4 | 2 |  |  | 12800 | 3100 |  | 15900
| 1.3.4 | Establish roster of communication experts to participate in CTRMs and CSM capacity building activities | SS | Staff time | 2 | 4 |  |  | 6400 | 6200 |  | 12600
| 1.3.5 | Develop criteria and TORs for communication focal points at regional and national levels | SS | Staff time | 2 |  |  |  | 6400 |  |  | 6400
| 1.3.6 | Identify and achieve buy-in of priority HBCs for intensification of CSM efforts, based on current and emerging documentation/data. | SS | Staff time | 4 | 4 |  |  | 12800 | 6200 |  | 19000
|  |  |  | Duty travel |  |  | 2 | 5000 |  |  | 10000 | 10000
| 1.3.7 | Conduct in-depth CSM needs assessment in selected HBCs | SS | Staff time | 16 | 12 |  |  | 51200 | 18600 |  | 69800
|  |  |  | Duty travel |  |  | 6 | 5000 |  |  | 30000 | 30000
|  |  |  | Meeting |  |  | 1 | 25000 |  |  | 25000 | 25000
|  |  |  | APW |  |  | 1 | 380000 |  |  | 380000 | 380000 | 380000
| 1.3.8 | Develop TORs and facilitate the formation of national CSM task forces in HBC/NTPs | SS | Staff time | 2 | 2 |  |  | 6400 | 3100 |  | 9500
| 1.3.9 | Coordinate preparation of plans for rapid capacity-building in selected HBCs | SS | Staff time | 16 | 12 |  |  | 51200 | 18600 |  | 69800
|  |  |  | Duty travel |  |  | 8 | 5000 |  |  | 40000 | 40000
|  |  |  | Meetings |  |  | 4 | 20000 |  |  | 80000 | 80000
|  |  |  | APW |  |  | 1 | 250000 |  |  | 250000 | 250000 | 250000
| 1.3.10 | Coordinate implementation of communication and capacity-building plans in priority HBCs, including training | SS | Staff time | 16 | 12 |  |  | 51200 | 18600 |  | 69800
|  |  |  | Duty travel |  |  | 8 | 5000 |  |  | 40000 | 40000
|  |  |  | Meetings |  |  | 4 | 20000 |  |  | 80000 | 80000
|  |  |  | APWs |  |  | 1 | 620000 |  |  | 620000 | 620000 | 620000
| 1.3.11 | Facilitate development of generic and country-specific tools and resources for CSM programming | SS | Staff time | 2 | 4 |  |  | 6400 | 6200 |  | 12600
|  |  |  | APW |  |  | 1 | 20000 |  |  | 20000 | 20000
| 1.3.12 | Technical assistance to ongoing CSM interventions in HBCs, including monitoring/review | SS | Staff time | 8 | 6 |  |  | 25600 | 9300 |  | 34900
| 1.3.13 | Comprehensive process/impact evaluation and documentation of the COMBI projects | SS | Staff time | 12 | 8 |  |  | 38400 | 12400 |  | 50800
|  |  |  | Duty travel |  |  | 4 | 5000 |  |  | 20000 | 20000
|  |  |  | APW |  |  | 1 | 50000 |  |  | 50000 | 50000
| 1.3.14 | Coordinate preparation and production of best practices document for TB-communication at country level | SS | Staff time | 4 | 8 |  |  | 12800 | 12400 |  | 25200
|  |  |  | Duty travel |  |  | 4 | 5000 |  |  | 20000 | 20000
|  |  |  | APW |  |  | 1 | 50000 |  |  | 50000 | 50000
|  | Sub-total | [6 empty] | 320000 | 130200 | 1775000 | 2225200 | 1250000
Information Products | 1.4.1 | Develop products in collaboration with partners and A/V unit of WHO, with clear marketing plans linked to A&C strategy and objectives | AC Officer | Staff time | 10 | 5 |  |  | 32000 | 7750 |  | 39750
|  |  |  | APWs |  |  | 4 | 25000 |  |  | 100000 | 100000
| 1.4.2 | Produce regular communiques for partners with preparatory steps for WTBD | AC Officer | Staff time | 5 |  |  |  | 16000 |  |  | 16000
| 1.4.3 | Coordinate production and distribution of WTBD information packet | AC Officer | Staff time | 5 | 2 |  |  | 16000 | 3100 |  | 19100
|  |  |  | APWs |  |  | 2 | 25000 |  |  | 50000 | 50000
| 1.4.4 | Coordinate production and distribution of World TB Day Highlights Report | AC Officer | Staff time | 2 | 1 |  |  | 6400 | 1550 |  | 7950
|  |  |  | APWs |  |  | 2 | 20000 |  |  | 40000 | 40000
| 1.4.5 | Coordinate development and use of facility with library manager and partners | AC Officer | Staff time | 3 | 1 |  |  | 9600 | 1550 |  | 11150
|  |  |  | APWs |  |  | 2 | 25000 |  |  | 50000 | 50000
| 1.4.6 | Production of press releases, advisories, briefing materials in collaboration with partners | AC Officer | Staff time | 5 |  |  |  | 16000 |  |  | 16000
|  |  |  | APWs |  |  | 8 | 10000 |  |  | 80000 | 80000
| 1.4.7 | Production of information for public events, advertisements, journal inserts | AC Officer | Staff time | 5 |  |  |  | 16000 |  |  | 16000
|  | Sub-total | [6 empty] | 112000 | 13950 | 320000 | 445950 | 0
|  | TOTAL FOR ADVOCACY AND COMMUNICATIONS | [6 empty] | 1116800 | 240250 | 3590000 | 4947050 | 2110000

## GDF 1 - COST
2. Global TB Drug Facility (GDF)
2.1 Application Review and Monitoring (ARM) - Costings
Products | No | Activities | Responsible Officer | Components | P - staff % of Time | G - staff % of Time | No. of visits or Units | Unit Cost | Staff cost |  | Cost of Activities | Planned Costs | For CB Decision
[5 empty] | 446 | 141.5 |  | 320000 | p
[8 empty] | 155000 |  | G
Demand assessment for GDF/GLC services (drugs, direct procurement and diagnostics) | 1.1.1 | Assess demand for first line TB drugs and resource gaps in priority countries | GA/EJ | Staff time | 1 |  |  |  | 3200 |  |  | 3200
(a) Contract demand assessment for 1st line TB drugs
| 1.1.2 | Assess demand for second line for TB drugs and resource gaps in priority countries | EJ | Staff time | 1 |  |  |  | 3200 |  |  | 3200
(a) Contract demand assessment for 2nd line TB drugs
| 1.1.3 | Assess demand for the Direct Procurement of second line TB drugs by international agencies including GFATM, World Bank, regional banks and other major donors | EJ | Staff time | 1 |  |  |  | 3200 |  |  | 3200
(a) Contract demand assessment for DP 2nd line
| 1.1.4 | Assess demand for the use of diagnostics for DOTS and DOTS plus |  | Staff time | 1 |  |  |  | 3200 |  |  | 3200
(a) Contract demand assessment for diagnostics
|  | Sub-total | [6 empty] | 12800 | 0 | 0 | 12800
Demand creation for GLC services (drugs, direct procurement and diagnostics) | 1.2.1 | Site visits to provide assistance needed | EJ | Staff time | 16 | 0 |  |  | 51200 | 0 |  | 51200
|  |  |  | Duty travel |  |  | 20 | 5000 |  |  | 100000 | 100000
|  | Sub-total | [6 empty] | 51200 | 0 | 100000 | 151200
Application and Review Process for GDF/GLC | 1.3.1 | Invite applications to GDF grants for first line TB drugs and diagnostics and for direct procurement | YG/EJ | Staff | 1 | 1 |  |  | 3200 | 1550 |  | 4750
| 1.3.2 | Coordinate GLC applications with GFATM |  | Staff time | 10 |  |  |  | 32000 |  |  | 32000
| 1.3.3 | Coordinate GDF applications with GFATM |  | Staff time | 1 |  |  |  | 3200 |  |  | 3200
| 1.3.4 | Screening of applications for first line grants and direct procurement |  | Staff time | 24 | 5 |  |  | 76800 | 7750 |  | 84550
| 1.3.5 | Screening of applications for second line grants and direct procurement |  | Staff time | 30 | 10 |  |  | 96000 | 15500 |  | 111500
| 1.3.6 | Review of grant applications by GDF TRC and coordinating Board |  | Staff time | 20 | 20 |  |  | 64000 | 31000 |  | 95000
|  | (a) Technical Review Committee meeting |  | Meeting |  |  | 4 | 50000 |  |  | 200000 | 200000
(b) MayeticVillage management (TRC)
(c) TRC minutes
(d) Joint TRC STB CB meetings
| 1.3.7 | Review of grants and direct procurement applications for second line drugs by the GLC |  | Staff time | 30 | 20 |  |  | 96000 | 31000 |  | 127000
|  |  |  | Meetings |  |  | 2 | 50000 |  |  | 100000 | 100000
| 1.3.8 | Country visits for GLC applications |  | Staff time | 30 | 15
| 1.3.9 | Country visits for GDF applications |  | Staff time | 35 | 7.5
|  | No. of travel of all GDF staff |  | Duty travel |  |  | 40 | 5000 |  |  | 200000 | 200000
| 1.3.10 | Letters of agreement for GLC |  | Staff time | 4 | 10 |  |  | 12800 | 15500 |  | 28300
| 1.3.11 | Grant agreements for GDF |  |  | 10 | 5 |  |  | 32000 | 7750 |  | 39750
| 1.3.12 | Technical Agreements for Direct Procurement |  | Staff time | 6 |  |  |  | 19200 |  |  | 19200
| 1.3.13 | Develop application mechanism for TB diagnostics |  | Staff time | 2 | 1 |  |  | 6400 | 1550 |  | 7950
|  | (a) Contract for the development for the application mechanism |  | Staff time | 20 | 10 |  |  | 64000 | 15500 |  | 79500
|  | Sub-total | [6 empty] | 505600 | 127100 | 500000 | 1132700
GDF/GLC monitoring review of GDF/GLC applications and review processes and documents | 1.4.1 | Follow up on recommendations from TRC and GLC (including nonapproved countries), country and monitoring visits | MA/EJ | Staff time | 20 | 10 |  |  | 64000 | 15500 |  | 79500
| 1.4.2 | GDF/GLC client survey - telephone project |  | Staff time | 2 | 2 |  |  | 6400 | 3100 |  | 9500
|  |  |  | Telephone calls |  |  | 1000 | 20 |  |  | 20000 | 20000
| 1.4.3 | Develop indicators to assess GDF/GLC impact on countries |  | Staff time | 4 |  |  |  | 12800 |  |  | 12800
| 1.4.4 | Develop standardised assessment tool for DOTS monitoring including GDF indicators |  | Staff time | 2 |  |  |  | 6400 |  |  | 6400
| 1.4.5 | Collect annual and quarterly reports |  | Staff time | 5 | 2 |  |  | 16000 | 3100 |  | 19100
| 1.4.6 | Monitoring missions to GLC approved projects |  | Duty travel (30 mission to travel by pair) | 15 | 5 | 30 | 10000 | 48000 | 7750 | 300000 | 355750
| 1.4.7 | Database and planner of GLC monitoring missions |  | Staff time | 2 |  |  |  | 6400 |  |  | 6400
| 1.4.8 | Monitoring missions to GDF supported countries |  | Duty travel | 30 | 7 | 30 | 5000 | 96000 | 10850 | 150000 | 256850
| 1.4.9 | Database and planner of GDF monitoring missions |  | Staff time | 1 |  |  |  | 3200 |  |  | 3200
| 1.4.10 | Assessement of monitoring dossier by GDF desk audit agency |  | Staff time | 15 | 2 |  |  | 48000 | 3100 |  | 51100
|  | (a) Contract with audit agencies |  | APW |  |  | 30 | 700 |  |  | 21000 | 21000
(b) mayeticVillage management (GDF desk audits)
| 1.4.11 | Review by TRC of monitoring dossier |  | Staff time | 18 |  |  |  | 57600 |  |  | 57600
| 1.4.12 | Review by GLC of the monitoring visit report |  | Staff time | 24 | 4 |  |  | 76800 | 6200 |  | 83000
| 1.4.13 | GDF grant agreements for 2nd and 3rd year |  | Staff time | 15 | 5 |  |  | 48000 | 7750 |  | 55750
| 1.4.14 | Management of country information including Country Overview speaedsheets and Monitoring Summary |  | Staff time | 16 | 0 |  |  | 51200 | 0 |  | 51200
| 1.4.15 | Develop GLC Project information spreadsheet |  | Staff time | 4 | 0 |  |  | 12800 | 0 |  | 12800
| 1.4.16 | Implement the GDF phase out strategy |  | Staff time | 4 |  |  |  | 12800 |  |  | 12800
| 1.4.17 | Review of GDF/GLC Monitoring processes and documents |  | Staff time | 20 |  |  |  | 64000 |  |  | 64000
| 1.4.18 | Participation in TBS country coordination meeting |  | Duty travel | 2 |  |  |  | 6400 |  |  | 6400
|  | Sub-total | [6 empty] | 636800 | 57350 | 491000 | 1185150
GDF phase out strategy | 1.5.1 | Establish a phase out strategy for the GDF |  | Staff time | 4 |  |  |  | 12800 |  |  | 12800
|  | Sub-total | [6 empty] | 12800 | 0 | 0 | 12800
|  | TOTAL FOR ARM | [6 empty] | 1219200 | 184450 | 1091000 | 2494650

## GDF 2 - COST
2. Global TB Drug Facility (GDF)
2.2 Supply (SUP) - Costings
Products | No | Activities | Responsible Officer | Components | P - staff % of Time | G - staff % of Time | No. of visits or Units | Unit Cost | Staff cost |  | Cost of Activities | Planned Costs | For CB Decision
[5 empty] | 182 |  |  | 320000 | P
[6 empty] | 90 |  | 155000 |  | G
Improved quality of 1st & 2nd line anti-TB drugs supplied globally | 1.1.1 | Commission, maintain and safeguard on-going pre-qualification project | RM/FJ | Staff time
| 1.1.2 | Issue fourth General Procurement Notice inviting expressions of interest (EOI) to supply first/second line anti-TB products | RM/FJ
|  | (a) Dissemination through regional offices, UN missions, STB partners |  | Staff time | 2 | 2 |  |  | 6400 | 3100 |  | 9500
|  | (b) Advertisements in journals/papers/websites |  | Staff time | 2 | 2 |  |  | 6400 | 3100 |  | 9500
|  |  |  | APW-Advertisement |  |  | 1 | 10000
| 1.1.3 | Receipt of EOIs and issuance of Guidelines for Dossier Submission by EDM/QSM | RM/FJ | Staff time | 2 | 4 |  |  | 6400 | 6200 |  | 12600
| 1.1.4 | Review of product dossiers from suppliers by EDM/QSM | RM/FJ | Staff time |  | 10 |  |  |  | 15500 |  | 15500
|  |  |  | APW |  |  | 2 | 100000 |  |  | 200000 | 200000
| 1.1.5 | GMP physical site audits of eligible manufacturers by EDM/QSM | RM/FJ | Staff time |  | 10 |  |  |  | 15500 |  | 15500
|  |  |  | APW |  |  | 2 | 175000 |  |  | 350000 | 350000
| 1.1.6 | Coordination with QSM | RM/FJ
|  | (a) New MoU for 2004/2005 |  | Staff time
|  | (b) Regular update meeting - 1/month |  | Staff time | 2 | 2 |  |  | 6400 | 3100 |  | 9500
|  | Sub-total | [6 empty] | 25600 | 46500 | 550000 | 622100
Efficient procurement and quality control of 2nd line anti-TB drugs through competitive selection of Procurement & Quality Control Agents for first & second line anti-TB drugs | 1.2.1 | Preparation of EOI for PRC Agents for 2nd line drugs | RM/FJ | Staff time | 2 | 2 |  |  | 6400 | 3100 |  | 9500
| 1.2.2 | Publication of EOI for PRC Agents for 2nd line drugs | RM/FJ
|  | (a) Dissemination through regional offices, UN missions, STB partners |  | Staff time | 2 | 4 |  |  | 6400 | 6200 |  | 12600
|  | (b) Advertisments in journals/papers/websites |  | Staff time |  | 4 |  |  |  | 6200 |  | 6200
|  | Advertisement |  | APW |  |  | 1 | 10000
| 1.2.3 | Receipt of EOIs and shortlisting | RM/FJ
|  | (a) Receive and file EOIs |  | Staff time |  | 4 |  |  |  | 6200 |  | 6200
|  | (b) Shortlist as per minimum criteria |  | Staff time | 2 | 2 |  |  | 6400 | 3100 |  | 9500
| 1.2.4 | Preparation of RFP for PRC Agents for 2nd line drugs and QC agents for 1st and 2nd line drugs | RM/FJ | Staff time | 8 | 2 |  |  | 25600 | 3100 |  | 28700
| 1.2.5 | Circulate RFP among STB partners for comment | RM/FJ | Staff time | 2 | 2 |  |  | 6400 | 3100 |  | 9500
| 1.2.6 | Issue RFP for PRC Agents for 2nd line drugs and QC agents for 1st & 2nd line drugs | RM/FJ
|  | (a) RFP sent to shortlisted agents |  | Staff time |  | 4 |  |  |  | 6200 |  | 6200
| 1.2.7 | Receipt of Proposals from potential PRC Agents for 2nd line drugs and potential QC agents for 1st & 2nd line drugs | RM/FJ
|  | (a) Convene Proposal opening committee, record and date Proposals received 2. Confirm receipt of each Proposal 3. Make copies of Proposals |  | Staff time |  | 2 |  |  |  | 3100 |  | 3100
|  | (b) Confirm receipt of each Proposal |  | Staff time |  | 2 |  |  |  | 3100 |  | 3100
|  | (c) Make copies of Proposals |  | Staff time |  | 2 |  |  |  | 3100 |  | 3100
| 1.2.8 | Adjudication of Proposals for PRC Agents PRC Agents for 2nd line drugs and QC agents for 1st & 2nd line drugs | RM/FJ
|  | (a) Select adjudication panel |  | Staff time | 2 |  |  |  | 6400 |  |  | 6400
|  | (b) Invite panel to Geneva and arrange TAs, meeting |  | Staff time |  | 2 |  |  |  | 3100 |  | 3100
|  |  |  | Meeting |  |  | 4 | 2500 |  |  | 10000 | 10000
|  | (c) Document adjudication outcome |  | Staff time | 2 |  |  |  | 6400 |  |  | 6400
|  | (d) Submit outcome and documentation of process to CRC for approval |  | Staff time | 2 |  |  |  | 6400 |  |  | 6400
|  | (e) Inform all proposers of outcome |  | Staff time |  |  | 2
| 1.2.9 | Contracting of new PRC Agents for 2nd line drugs and QC agents for 1st & 2nd line drugs | RM/FJ | Staff time
|  | (a) Negotiations with selected agents |  | Staff time | 2 |  |  |  | 6400 |  |  | 6400
|  | (b) Drafting of contract |  | Staff time | 4 |  |  |  | 12800 |  |  | 12800
|  | (c) Submission of draft to CRC |  | Staff time | 2 |  |  |  | 6400 |  |  | 6400
|  | (d) Finalization of draft |  | Staff time | 2 |  |  |  | 6400 |  |  | 6400
|  | (e) Signing of final contracts |  | Staff time | 2 |  |  |  | 6400 |  |  | 6400
|  | Sub-total | [6 empty] | 108800 | 49600 | 10000 | 168400
Timely supply of second line anti-TB drugs (IDA) | 1.3.1 | Monitor order requests and placement by projects to procurement agent | RM/FJ
|  | (a) Verify quantities ordered match quantities approved per project |  | Staff time | 10 | 1 |  |  | 32000 | 1550 |  | 33550
|  | (b) Ensure Eli Lilly drugs distributed to all projects |  | Staff time | 10 | 2 |  |  | 32000 | 3100 |  | 35100
| 1.3.2 | Shipping and freight to projects | RM/FJ | Staff time | 4 |  |  |  | 12800 |  |  | 12800
| 1.3.3 | Negotiations with Eli Lilly for second half of 2004 | RM/FJ/EJ | Staff time | 2 |  |  |  | 6400 |  |  | 6400
|  | Sub-total | [6 empty] | 83200 | 4650 | 0 | 87850
Improved effciency and quality of supply of second line anti-TB drugs (New PA) | 1.4.1 | Preparation of Invitation to Bid (ITB) | RM/FJ | Staff time | 2 | 1 |  |  | 6400 | 1550 |  | 7950
|  | (a) Comments on Draft ITB to PA |  | Staff time | 4 | 2 |  |  | 12800 | 3100 |  | 15900
(b) Finalization of ITB by PA
| 1.4.2 | Issuance of ITB to pre-qualified manufacturers | RM/FJ
| 1.4.3 | Adjudication of Bids | RM/FJ
|  | (a) Assist with selection of adjudication panel |  | Staff time | 2 | 2 |  |  | 6400 | 3100 |  | 9500
|  | (b) Arrange for panel to meet with PA for adjudication |  | Staff time |  | 2 |  |  |  | 3100 |  | 3100
|  |  |  | Meeting |  |  | 1 | 10000 |  |  | 10000 | 10000
| 1.4.4 | Contracting of new manufacturers | RM/FJ/HV | Staff time
| 1.4.5 | Establishment of stockpile for 2nd line anti-TB drugs | RM/FJ | Staff time | 4 | 2 |  |  | 12800 | 3100 |  | 15900
| 1.4.6 | Monitor order requests and placement by projects to procurement agent | RM/FJ
|  | (a) Verify quantities ordered match quantities approved per project |  | Staff time | 6 |  |  |  | 19200 |  |  | 19200
|  | (b) Ensure Eli Lilly drugs distributed to all projects |  | Staff time | 6 |  |  |  | 19200 |  |  | 19200
|  | (c) Cost of drugs (for grants) |  | Drugs |  |  | 1 | 1400000 |  |  | 1400000 | 1400000
|  | (d) Sub-contract for QC and PSI (for grants) |  | Drugs - QC & PSI (4% of drug cost) |  |  | 1 | 56000 |  |  | 56000 | 56000
|  | (e) Cost for insurance, shipping and freight (for grants) |  | Drugs-Ins and freight(13% of drug cost) |  |  | 1 | 182000 |  |  | 182000 | 182000
| 1.4.7 | Quality control and pre-shipment inspection | RM/FJ
|  | (a) Comments on QC agent remarks |  | Staff time | 4 |  |  |  | 12800 |  |  | 12800
| 1.4.8 | Shipping and freight to projects | RM/FJ | Staff time | 4 |  |  |  | 12800 |  |  | 12800
|  | Sub-total | [6 empty] | 102400 | 13950 | 1648000 | 1764350
Efficient supply of quality first line anti-TB drugs | 1.5.1 | Placing orders with PA for grants and direct procurement using UNWEBBUY system | RM | Staff time | 4 | 4 |  |  | 12800 | 6200 |  | 19000
|  | (a) Cost of drugs |  | Drugs |  |  | 1 | 55000000 |  |  | 55000000 | 55000000
|  | (b) Sub-contract for QC and PSI |  | Drugs-QC & PSI (4% of drug cost) |  |  | 1 | 2200000 |  |  | 2200000 | 2200000
|  | (c) Cost for insurance, shipping and freight |  | Drugs - Ins and freight (13% of drug cost) |  |  | 1 | 7150000 |  |  | 7150000 | 7150000
| 1.5.2 | Quality control and pre-shipment inspection | RM | Staff time | 4 |  |  |  | 12800 |  |  | 12800
|  | (a) Comments on QC agent remarks |  | Drugs(part of cost of drugs) | 4 |  |  |  | 12800 |  |  | 12800
| 1.5.3 | Shipping and freight to projects | RM | Drugs(part of cost of drugs) | 4 |  |  |  | 12800 |  |  | 12800
|  | Sub-total | [6 empty] | 51200 | 6200 | 64350000 | 64407400
Improved delivery lead times and monitoring of supply through close coordination of supply agents for first line drugs and effective management of anti-TB drugs stockpile(s) | 1.6.1 | Regular communication and video conferences | RM | Staff time | 4 | 1 |  |  | 12800 | 1550 |  | 14350
|  |  |  | Misc-videoconferences |  |  | 24 | 1000 |  |  | 24000 | 24000
|  | (a) Booking of conference facilities |  | Staff time |  | 2 |  |  |  | 3100 |  | 3100
| 1.6.2 | Super Team' meetings with contractual partners for supply | RM | Meeting |  |  | 6 | 15000 |  |  | 90000 | 90000
|  | (a) Arrange TAs fro participation in meetings |  | Staff time |  | 2 |  |  |  | 3100 |  | 3100
|  | (b) Finalize minutes and action points |  | Staff time | 20 |  |  |  | 64000 |  |  | 64000
| 1.6.3 | Updated online monitoring systems, financial and technical reports | RM
|  | (a) Monitor and comment on reports |  | Staff time | 8 |  |  |  | 25600 |  |  | 25600
0
Improved delivery lead times and monitoring of supply through close coordination of supply agents for second line drugs and effective management of anti-TB drugs stockpile(s) | 1.6.4 | Regular meetings with PA (IDA) | RM/FJ | Staff time | 3 |  |  |  | 9600 |  |  | 9600
|  |  |  | Duty travel |  |  | 3 | 5000 |  |  | 15000 | 15000
|  | (a) Arrange TAs |  | Staff time |  | 3 |  |  |  | 4650 |  | 4650
|  | (b) Finalize minutes and action points |  | Staff time | 2 |  |  |  | 6400 |  |  | 6400
| 1.6.5 | Super Team' meetings with contractual partners for supply (New Partners) | RM/FJ | Meeting |  |  | 4 | 10000 |  |  | 40000 | 40000
|  | (a) Arrange TAs fro participation in meetings |  | Staff time |  | 4 |  |  |  | 6200 |  | 6200
|  | (b) Finalize minutes and action points |  | Staff time | 15 |  |  |  | 48000 |  |  | 48000
| 1.6.6 | Financial and technical reports | RM/FJ
|  | (a) Monitor and comment on reports |  | Staff time | 5 |  |  |  | 16000 |  |  | 16000
Accurate forecast of Anti-TB drugs needs for 1st and second line drugs | 1.6.7 | Annual forecast | RM/FJ/EJ/LA | Staff time | 2 |  |  |  | 6400 |  |  | 6400
| 1.6.8 | Quarterly forecasts | RM/FJ/EJ/LA | Staff time | 3 |  |  |  | 9600 |  |  | 9600
|  | Sub-total | [6 empty] | 198400 | 18600 | 169000 | 386000
Develop procurement and distribution strategy for TB diagnostics and laboratory equipment for TB and MDR-TB treatment | 1.7.1 | Determine specifications of diagnostics and laboratory equipments to be supplied by GDF / GLC | HV/FJ |  | 3 |  |  |  | 9600 |  |  | 9600
| 1.7.2 | Procure and supply diagnostics and laboratory equipment for TB and MDR-TB treatment | HV/FJ |  | 1 |  |  |  | 3200 |  |  | 3200
|  | Sub-total | [6 empty] | 12800 | 0 | 0 | 12800
|  | TOTAL FOR SUP | [6 empty] | 582400 | 139500 | 66727000 | 67448900

## GDF 3 - COST
2. Global TB Drug Facility (GDF)
2.3 Drug Management (DM) - Costings
Products | No | Activities | Responsible Officer | Components | P - staff % of Time | G - staff % of Time | No. of visits or Units | Unit Cost | Staff cost |  | Cost of Activities | Planned Costs | For CB Decision
[5 empty] | 32 |  |  | 320000 | P
[6 empty] | 4 |  | 155000 |  | G
Improved national and international TB drug Manufacturing | 1.1.1 | Catalyze participation of National Drug Manufactures in Pre-qualification projects | HV/FJ | Staff time | 2 | 1 |  |  | 6400 | 1550 |  | 7950
| 1.1.2 | Catalyze Drug Quality Assurance activities | EDM/QSM | Staff time
|  | (a) Participate in initatives in QA |  | Staff time | 2 | 1 |  |  | 6400 | 1550 |  | 7950
|  | (b) Promote test lab peer supervision and standard setting |  | Staff time | 2 | 1 |  |  | 6400 | 1550 |  | 7950
|  | (c) Share QA problems with concerned WHO sections |  | Staff time | 1 |  |  |  | 3200 |  |  | 3200
|  | (d) Participate in QA workshops and conferences |  | Staff time | 2 |  |  |  | 6400 |  |  | 6400
|  |  |  | Duty travel |  |  | 4 | 2500 |  |  | 10000 | 10000
|  | Sub-total | [6 empty] | 28800 | 4650 | 10000 | 43450
Update TB drug market survey report | 1.2.1 | Produce, distribute and analyse questionnaire Include 2nd line drugs | HV/FJ | Staff time | 3 | 1 |  |  | 9600 | 1550 |  | 11150
|  | Sub-total | [6 empty] | 9600 | 1550 | 0 | 11150
Improve Drug Management in GDF/GLC supported countries | 1.3.1 | Catalyze Regional TB drug management meetings and other DM activities/training | HV/FJ | Staff time | 2 |  |  |  | 6400 |  |  | 6400
| 1.3.2 | Develop an external partner co-ordination mechanism | HV | Staff time | 1 |  |  |  | 3200 |  |  | 3200
| 1.3.3 | Develop and implement a mechanism to ensure that recommendations from GLC working group, TRC, Country visit, monitoring visit are followed up by the elevant partners | HV | Staff time | 5 |  |  |  | 16000 |  |  | 16000
| 1.3.4 | Include DM activities for 2nd line TB treatment in WHO publications | HV | Staff time | 1 |  |  |  | 3200 |  |  | 3200
|  | Sub-total | [6 empty] | 28800 | 0 | 0 | 28800
Data base and planner of GDF / GLC monitoring missions | 1.4.1 | Country visits to include standardised DM data collection and DM discussion topics | MA/FJ | Staff time | 1 |  |  |  | 3200 |  |  | 3200
| 1.4.2 | Participate in monitoring missions to GDF/GLC supported countries |  | Duty travel |  |  | 4 | 2500 |  |  | 10000 | 10000
| 1.4.3 | Training of consultants |  | APW |  |  | 1 | 10000 |  |  | 10000 | 10000
|  |  |  | STC |  |  | 1 | 10000 |  |  | 10000 | 10000
| 1.4.4 | GDF Grant Agreements and GLC Letter of Agreement to include DM development goals |  | Staff time | 1 |  |  |  | 3200 |  |  | 3200
| 1.4.5 | GDF Grant Agreements and GLC Letter of Agreement to include DM partners and assistance |  | Staff time | 1 |  |  |  | 3200 |  |  | 3200
|  | Sub-total | [6 empty] | 9600 | 0 | 30000 | 39600
To develop a monitoring system for procurement and consumption of second line drugs | 1.5.1 | Implementation of the system to the point of consumption | FJ |  | 5 |  |  |  | 16000 |  |  | 16000
| 1.5.2 | Development of monitoring system | FJ
| 1.5.3 | Track the drugs since the order to the point of consumption | FJ
|  | Sub-total | [6 empty] | 16000 | 0 | 0 | 16000
Strategy development in collaboration with DEWG to promote in-country 1st & 2nd line TB drug management | 1.6.1 | Develop and field test a TB drug flow critical path incl. all aspects of DM for NTP | HV/TM | APW |  |  | 4 | 5000 |  |  | 20000 | 20000
| 1.6.2 | Monitor implementation of TB drug management plans | HV | Duty travel |  |  | 4 | 5000 |  |  | 20000 | 20000
|  | Sub-total | [6 empty] | 0 | 0 | 40000 | 40000
Facilitate incorporation of Drug Management plans into DOTS expansion plans | 1.7.1 | Involve partners systematically in DM of countries receiving 1st and 2nd line drugs from GDF/GLC | HV/FJ | Staff time
| 1.7.2 | Paper on DM for 1st line anti-TB drugs, briefing for in country visits, base line for 1st and 2nd monitoring visits, facilitation training in DM issues, Capacity building for phase out strategy | TM | APW |  |  | 1 | 10000 |  |  | 10000 | 10000
| 1.7.3 | Paper on DM for 2nd line anti-TB drugs, briefing for in country visits, base line for 1st and 2nd monitoring visits, facilitation training in DM issues, Capacity building for phase out strategy | HV/FJ | APW |  |  | 1 | 10000 |  |  | 10000 | 10000
|  | Sub-total | [6 empty] | 0 | 0 | 20000 | 20000
Strategy development in collaboration with DEWG and EDM to promote use of FDCs | 1.8.1 | Catalyse training on introduction of FDCs in TB program | HV | Meeting | 2 |  |  |  | 6400 |  |  | 6400
| 1.8.2 | Coordinate printing-French and Russion version of FDC guide | HV/FJ | APW |  |  | 1 | 5000 |  |  | 5000 | 5000
| 1.8.3 | Regular meetings with DEWG and/or EDM on DM and TB product issues | HV/FJ | Staff time | 1 |  |  |  | 3200 |  |  | 3200
|  | Sub-total | [6 empty] | 9600 | 0 | 5000 | 14600
|  | TOTAL FOR DM | [6 empty] | 102400 | 6200 | 105000 | 197600

## GDF 4 - COST
2. Global TB Drug Facility (GDF)
2.4 General Management and Support (GMS) - Costings
Products | No | Activities | Responsible Officer | Components | P - staff % of Time | G - staff % of Time | No. of visits or Units | Unit Cost | Staff cost |  | Cost of Activities | Planned Costs | For CB Decision
[5 empty] | 257 |  |  | 320000 | P
[6 empty] | 76 |  | 155000 |  | G
GDF Public Relations (Global) | 1.1.1 | Branding of GDF: market GDF brand as one of the most efficient, innovative and effective global health mechanisms available | AC Officer | Staff time of AC Officer in Sec 1.4 | 0 |  |  |  | 0 |  |  | 0
| 1.1.2 | Internal PR: Active campaign to advocate GDF a) Internal audience b) External audience | All TBP | Staff time of AC Officer in Sec 1.4
| 1.1.3 | Presentations on GDF to key stakeholders | All TBP | Staff time of AC Officer in Sec 1.4 | 0 |  |  |  | 0 | 0 |  | 0
| 1.1.4 | GDF Road show to key partners/donors (TA's) | GDF | Duty travel |  |  | 12 | 5000 |  |  | 60000 | 60000
| 1.1.5 | Monthly updates on GDF to Stop TB Coordinating Board, Regional Offices and Country WHO Offices | GDF VA | Staff time of AC Officer in Sec 1.4 | 0 |  |  |  | 0 | 0 |  | 0
| 1.1.6 | Publish GDF newsletter - 2 issues and distribute to all partners in GDF operational areas | GDF/AC Officer | Staff time of AC Officer in Sec 1.4 | 0 |  |  |  | 0 | 0 |  | 0
|  | Cost of development and printing |  | APW |  |  | 1 | 20000 |  |  | 20000 | 20000
|  | Cost of distribution |  | Misc-mailing |  |  | 24 | 1000 |  |  | 24000 | 24000
| 1.1.7 | Develop a follow up video from Moldova (end of story) | GDF/AC Officer | Staff time of AC Officer in Sec 1.4 | 0 |  |  |  | 0 | 0 |  | 0
|  | Cost of development, filming and post production |  | APW |  |  | 1 | 20000 |  |  | 20000 | 20000
| 1.1.8 | Improve GDF advocacy pack | GDF/AC Officer | Staff time of AC Officer in Sec 1.4 | 0 |  |  |  | 0 | 0 |  | 0
|  | Fact sheets, CD and video |  | APW |  |  | 1 | 10000 |  | 0 | 10000 | 10000
| 1.1.9 | Enhancement, marketing and translation of GDF website | IT Officer/AC Officer | Staff time of AC Officer in Sec 1.4 | 0 |  |  |  | 0 | 0 |  | 0
|  |  |  | APW |  |  | 1 | 20000 |  |  | 20000 | 20000
| 1.1.10 | Prepare a proposal to increase budget for advocacy and brand building to cover GDF specific needs | GDF/PRA/ AC Officer | Staff time of AC Officer in Sec 1.4 | 0 |  |  |  | 0 | 0 |  | 0
| 1.1.11 | Publicity linking DOTS and GDF | GDF/AC Officer | Staff time of AC Officer in Sec 1.4 | 0 |  |  |  | 0 | 0 |  | 0
|  | Consultant to develop a paper |  | Consultant (4 months) |  |  | 4 | 12500 |  |  | 50000 | 50000
| 1.1.12 | Develop and implement a strategy to undo negative/incorrect perceptions about GDF | GDF/AC Officer | Staff time of AC Officer in Sec 1.4 | 0 |  |  |  | 0 | 0 |  | 0
| 1.1.13 | Run a Political advocacy and lobbying campaign (eg.letters from patients in GDF documents who have received cheap drugs to patients in countries with expensive drugs) | GDF/AC Officer | Staff time of AC Officer in Sec 1.4 | 0 |  | 1 | 50000 | 0 | 0 | 50000 | 50000
|  | Hire a lobbyist |  | Consultant(4 months) |  |  | 4 | 12500 |  | 0 | 50000 | 50000
| 1.1.14 | Media and journal coverage - develop new angles on the GDF and provide these to journalists and medical journals to ensure it is covered in global and medical media. | GDF/AC Officer | Staff time of AC Officer in Sec 1.4 | 0 |  |  |  | 0 | 0 |  | 0
| 1..1.15 | Establish a recording system of GDF pressclippings | GDF/AC Officer | Staff time of AC Officer in Sec 1.4 | 0 |  |  |  | 0 | 0 |  | 0
| 1.1.16 | Hire political lobbyist to lobby to the Global Fund on behalf of GDF | GDF/AC Officer | Staff time of AC Officer in Sec 1.4 | 0 |  |  |  | 0 |  |  | 0
|  | Hire a political lobbyist |  | Consultant(4 months) |  |  | 4 | 12500 |  |  | 50000 | 50000
| 1.1.17 | Add advocacy materials to drug shipments | GDF/IAPSO
| 1.1.18 | Plan for joint adctivities for other disease GDF's (strategy paper) | AC Team
|  | Sub-total | [6 empty] | 0 | 0 | 354000 | 354000
Service promotion (Grant Advocacy) | 1.2.1 | Identify regional and country GDF representatives/ambassadors | GDF ARM YG | Staff time | 2 |  |  |  | 6400 |  |  | 6400
| 1.2.2 | Identify NGO list servers to add links to GDF website and application form |  | Staff time | 2 |  |  |  | 6400 |  |  | 6400
| 1.2.3 | Presentations at conferences and meetings to encourage STB partners to promote GDF grant applications (TA) | GDF ARM | Staff time | 6 |  |  |  | 19200 |  |  | 19200
|  | Attendance to meetings and conferences |  | Duty travel |  |  | 24 | 5000 |  |  | 120000 | 120000
| 1.2.4 | Prepare advocacy paper for NTP/WR's briefing on process and asking for assistance/ names of partners in country | GDF ARM | Staff time | 4 |  |  |  | 12800 |  |  | 12800
| 1.2.5 | Build strategy to approach countries on behalf of GDF | GDF ARM | Staff time | 4 |  |  |  | 12800 |  |  | 12800
|  | Sub-total | [6 empty] | 57600 | 0 | 120000 | 177600
Service promotion (Direct Procurement Advocacy) | 1.3.1 | Implement DP developed in collaboration with Procter and Gamble | GDF SUP RM | Staff time | 4 |  |  |  | 12800 |  |  | 12800
| 1.3.2 | Educate regional and country GDF ambassadors on DP through teleconferences, videoconferences, presentations etc | GDF SUP RM | Staff time | 4 |  |  |  | 12800 |  |  | 12800
|  | Cost of telephone calls and video conferences |  | Misc. expenses |  |  | 24 | 1000 |  |  | 24000 | 24000
| 1.3.3 | Include DP advocacy as part of all country visit missions | GDF SUP RM | Supplies | 4 |  |  |  | 12800 |  |  | 12800
| 1.3.4 | Improved advocacy for UN WEBBUY | GDF SUP RM | Staff time | 2 |  |  |  | 6400 |  |  | 6400
|  | Sub-total | [6 empty] | 44800 | 0 | 24000 | 68800
Service promotion (Product Advocacy) | 1.4.1 | Brand GDF drugs and patient kits and blister packs (WORK WITH P+G and external agencies) | HV | Staff time | 2 |  |  |  | 6400 |  |  | 6400
| 1.4.2 | Improved advocacy on rational for GDF standardization | HV/AC Officer | Staff time | 2 |  |  |  | 6400 |  |  | 6400
| 1.4.3 | Develop a marketing strategy for GDF products such as patient kits and blister packs | HV/AC Officer | Consultant (no. of months) |  |  | 1 | 20000 |  |  | 20000 | 20000
|  | Sub-total | [6 empty] | 12800 | 0 | 20000 | 32800
Service promotion (Whitelist Advocacy) | 1.5.1 | Develop a marketing and branding strategy for GDF prequalification service | GDF SUP RM | Consultant (no. of months) |  |  | 1 | 10000 |  |  | 10000 | 10000
|  | Sub-total | [6 empty] | 0 | 0 | 10000 | 10000
Resource mobilisation | 1.6.1 | Search for new donors | Exec Sec | Staff time | 25 |  |  |  | 80000 |  |  | 80000
| 1.6.2 | Improve financial statements and reporting | LA/PRA | Staff time | 4 |  |  |  | 12800 |  |  | 12800
| 1.6.3 | Assign CB member for fund raising | Exec Sec | Staff time | 2 |  |  |  | 6400 |  |  | 6400
| 1.6.4 | Create a budget for resource mobilization | Exec Sec | Duty travel | 2 |  |  |  | 6400 |  |  | 6400
| 1.6.5 | Update funding gap regularly - identifying demand for first and second line drugs and fund raise accordingly | GDF | Staff time | 0 |  |  |  | 0 |  |  | 0
| 1.6.6 | Develop a donor pack and promote to pre-qualified pharmaceutical companies who may be interested making drug donations for the GDF | PRA | Staff time of PRA in Sec 3.1 | 0 |  |  |  | 0 |  |  | 0
| 1.6.7 | Develop a donor pack and promote to the corporate sector selling the GDF in language they can understand. | PRA | Staff time | 0 |  |  |  | 0 |  |  | 0
| 1.6.8 | Develop a paper with key talking points on the GDF for business leaders to encourage them to act as effective advocates. | PRA GDF staff | Staff time of PRA in Sec 3.1 | 0 |  |  |  | 0 |  |  | 0
| 1.6.9 | Identify group of corportate leaders to serve as advisors and global advocates of GDF | Exec Sec | Staff time | 4 |  |  |  | 12800 |  |  | 12800
| 1.6.10 | One page paper illustrating the differences between the Global Fund and the GDF for donors. | GDF | Staff time | 0 |  |  |  | 0 |  |  | 0
|  | Sub-total | [6 empty] | 118400 | 0 | 0 | 118400
Internal management | 1.7.1 | Management of GDF resources, products and activities | GDF VA | Staff time | 100 | 30 |  |  | 320000 | 46500 |  | 366500
| 1.7.2 | 6 monthly retreats to strategise on workplan | All GDF staff | Meeting |  |  | 4 | 1000 |  |  | 4000 | 4000
| 1.7.3 | Staff meetings every week | All GDF staff | Staff time | 4 |  |  |  | 12800 |  |  | 12800
| 1.7.4 | Country support meeting every week | ARM team | Staff time | 4 |  |  |  | 12800 |  |  | 12800
| 1.7.5 | Supply team meeting every week | SUP team | Staff time | 4 |  |  |  | 12800 |  |  | 12800
| 1.7.6 | A&C meeting every week (include A&C TBP) | GDF/A&C team | Staff time | 4 |  |  |  | 12800 |  |  | 12800
| 1.7.7 | Review of annual work plans and budgets | All GDF staff | Staff time | 10 | 2 |  |  | 32000 | 3100 |  | 35100
| 1.7.8 | Semi-annual reports and interim financial reports on GDF progress and performance | VA/LA | Staff time | 10 | 8 |  |  | 32000 | 12400 |  | 44400
| 1.7.9 | Monitor all work with WHO to ensure that it adheres to the MOU. | GDF Manager | Staff time | 2 |  |  |  | 6400 |  |  | 6400
| 1.7.10 | Training for all GDF staff in AMS and MSU services | All GDF staff | Staff time | 2 | 2 |  |  | 6400 | 3100 |  | 9500
| 1.7.11 | Organize and secure budget for staff rotations for GDF staff to partner organisations | All GDF staff | Staff time | 1 | 4 |  |  | 3200 | 6200 |  | 9400
| 1.7.12 | Include individual training needs as part of all PMDS forms | All GDF staff | Staff time | 1 | 4 |  |  | 3200 | 6200 |  | 9400
| 1.7.13 | Monthly financial updates | LA | Staff time | 2 | 2 |  |  | 6400 | 3100 |  | 9500
| 1.7.14 | Secure 3 fixed term posts for GDF P staff and 3 fixed term posts for GDF G staff ensure that post level adequately reflects actual work for all ST staff | Exec Sec | Staff time | [7 empty] | 0
|  | Sub-total | [6 empty] | 460800 | 80600 | 4000 | 545400
Information management | 1.8.1 | Review and enhance standard operating procedures for GDF activities | IT Officer | Staff time | 24 | 8 |  |  | 76800 | 12400 |  | 89200
| 1.8.2 | Implement phase 1 of info management system | All GDF staff | Staff time | 8 | 8 |  |  | 25600 | 12400 |  | 38000
| 1.8.3 | Implement Phase 2 | All GDF staff | Staff time | 8 | 8 |  |  | 25600 | 12400 |  | 38000
| 1.8.4 | All GDF staff to use AOL IM | All GDF staff | Staff time
|  | Sub-total | [6 empty] | 128000 | 37200 | 0 | 165200
|  | TOTAL FOR GMS | [6 empty] | 822400 | 117800 | 532000 | 1472200

## ADM-RM COSTING
3. GENERAL MANAGEMENT AND ADMINISTRATION (GMA)
3.1 Resource Mobilization and Financial Management (RMF) - Costings
Products | No | Activities | Responsible Officer | Components | P - staff % of Time | G - staff % of Time | No. of visits or Units | Unit Cost | Staff cost |  | Cost of Activities | Planned Costs | For CB Decision
[5 empty] | 155 |  |  | 320000 | P
[6 empty] | 93 |  | 155000 |  | G
Resource Mobilization and Financial Management | 1.1.1 | Resource Mobilization Directory on-line. Projects updated quarterly | PRA IT | Staff time | 10 | 40 |  |  | 32000 | 62000 |  | 94000
| 1.1.2 | Partnership Financial Monitoring | PRA IT | Staff time | 15 | 5 |  |  | 48000 | 7750 |  | 55750
|  |  |  | APW |  |  | 1 | 20000 |  |  | 20000 | 20000
| 1.1.3 | Partnership Financial Projections | PRA | Staff time | 10 | 5 |  |  | 32000 | 7750 |  | 39750
| 1.1.4 | Donor outreach and donor management | PRA A&C | Staff time | 25 | 10 |  |  | 80000 | 15500 |  | 95500
|  |  |  | Duty travel |  |  | 24 | 5000 |  |  | 120000 | 120000
| 1.1.5 | Facilitation of pooled partnership funds | PRA LA | Staff time | 25 | 5 |  |  | 80000 | 7750 |  | 87750
| 1.1.6 | Secretariat Financial Reporting | Lina | Staff time | 50 | 25 |  |  | 160000 | 38750 |  | 198750
| 1.1.7 | Linkage with Resource Mobilization "clients" such as WGs, GDF | PRA Sarah Gini | Staff time | 10 | 1 |  |  | 32000 | 1550 |  | 33550
| 1.1.8 | Linkage with Partnership and Advocacy and Communications | PRA AC Officer | Staff time | 5 | 1 |  |  | 16000 | 1550 |  | 17550
|  | Pack production |  | APW |  |  | 1 | 30000 |  |  | 30000 | 30000
| 1.1.9 | Review and update of Resource Mobilization strategy as needed | Exec Sec PRA AC Officer IT | Staff time | 5 | 1 |  |  | 16000 | 1550 |  | 17550
|  | Sub-total | [6 empty] | 496000 | 144150 | 170000 | 810150
#VALUE!
Staff time
Staff time

## ADM-IT COSTING
3. GENERAL MANAGEMENT AND ADMINISTRATION (GMA)
3.2 Information Management (IM) - Costings
Products | No | Activities | Responsible Officer | Components | P - staff % of Time | G - staff % of Time | No. of visits or Units | Unit Cost | Staff cost |  | Cost of Activities | Planned Costs | For CB Decision
[5 empty] | 106 |  |  | 320000 | P
[6 empty] | 22 |  | 155000 |  | G
Information Tools | 1.1.1 | Regular review of needs and maintenance of IT products and contents | IT Officer | Staff time | 24 | 2 |  |  | 76800 | 3100 |  | 79900
| 1.1.2 | Documents management system-hard copy and electronic (IRIMS) |  | Staff time | 20 | 20 |  |  | 64000 | 31000 |  | 95000
| 1.1.3 | IT tools updates, including website |  | Staff time | 25 |  |  |  | 80000 |  |  | 80000
| 1.1.4 | IT support to database development and linkages |  | Staff time | 25 |  |  |  | 80000 |  |  | 80000
|  |  |  | APW |  |  | 2 | 20000 |  |  | 40000 | 40000
| 1.1.5 | Website software and server hosting |  | Staff time | 5 |  |  |  | 16000 |  |  | 16000
|  |  |  | S&E |  |  | 1 | 100000 |  |  | 100000 | 100000
| 1.1.6 | Information system products (software and implementation support) |  | Staff time | 2 |  |  |  | 6400 |  |  | 6400
|  |  |  | S&E |  |  | 1 | 50000 |  |  | 50000 | 50000
| 1.1.7 | Collaborative working tool (Mayetic Vilage) |  | Staff time | 5 |  |  |  | 16000 |  |  | 16000
|  |  |  | APW |  |  | 1 | 20000 |  |  | 20000 | 20000
|  | Sub-total | [6 empty] | 339200 | 34100 | 210000 | 583300

## ADM-GM COSTING
3. GENERAL MANAGEMENT AND ADMINISTRATION (GMA)
3.3 General Administration (GA) - Costings
Products | No | Activities | Responsible Officer | Components | P - staff % of Time | G - staff % of Time | No. of visits or Units | Unit Cost | Staff cost |  | Cost of Activities | Planned Costs | For CB Decision
[5 empty] | 82 |  |  | 320000 | P
[6 empty] | 105 |  | 155000 |  | G
Office management | 1.1.1 | Secretariat operations | Exec Secr | Staff time | 20 |  |  |  | 64000 |  |  | 64000
|  | Mailing, postage and other miscellaneous expenses for two years |  | Miscellaneous |  |  | 2 | 25000 |  |  | 50000 | 50000
| 1.1.2 | Coordination of support to staff within the secretariat | Exec Secr | Staff time | 10 | 20 |  |  | 32000 | 31000 |  | 63000
| 1.1.3 | Standard administrative operating procedures | Lina | Staff time | 10 | 5 |  |  | 32000 | 7750 |  | 39750
| 1.1.4 | Office space and equipment | Mary/Sulo | Staff time |  | 5 |  |  |  | 7750 |  | 7750
|  |  |  | S&E |  |  | 1 | 50000 |  |  | 50000 | 50000
| 1.1.5 | Recruitment of personnel | Exec Secr and Mary | Staff time | 20 | 50 |  |  | 64000 | 77500 |  | 141500
| 1.1.6 | Internship and exchange programmes | Exec Sec, | Staff time |  | 5 |  |  |  | 7750 |  | 7750
| 1.1.7 | Secondments to and from Secretariat and Partners | Exec Sec. | Staff time | 5 | 5 |  |  | 16000 | 7750 |  | 23750
| 1.1.8 | Staff development | All Secretariat staff | Staff time | 10 | 10 |  |  | 32000 | 15500 |  | 47500
| 1.1.9 | PMDS | All Secretariat staff | Staff time | 2 | 2 |  |  | 6400 | 3100 |  | 9500
| 1.1.10 | Coordination with the legal counsel on all contracts issued funded by contributions channelled from other sources | Exec Sec. | Staff time | 4 | 2 |  |  | 12800 | 3100 |  | 15900
|  |  |  | APW |  |  | 1 | 20000 |  |  | 20000 | 20000
| 1.1.11 | Retreat twice a year to enhance team building within the secretariat and possibly with active partners and other social activities | Sulo | Staff time | 1 | 1 |  |  | 3200 | 1550 |  | 4750
|  | Retreat costs |  | Meetings |  |  | 4 | 5000 |  |  | 20000 | 20000
|  | TOTAL FOR GA | [6 empty] | 262400 | 162750 | 140000 | 565150

## 2004-2005WP
DIVISION OF WORKPLAN BY YEAR
No. | Components | Areas of work | P-Staff | G-Staff | Staff Costs | Activity costs | Total Planned costs | 2004 | 2005
1 | Support and Innovations | 1.1 Governance | 387200 | 12400 | 399600 | 1144000 | 1543600 | 771800 | 771800
| (S&I) | 1.2 Coordination and Growth | 316800 | 94550 | 411350 | 2400000 | 2811350 | 1405675 | 1405675
|  | 1.3 Working Groups | 563200 | 148800 | 712000 | 770000 | 1482000 | 741000 | 741000
|  | 1.4 Communications and Advocacy | 1116800 | 240250 | 1357050 | 3590000 | 4947050 | 2473525 | 2473525
|  | Sub-total | 2384000 | 496000 | 2880000 | 7904000 | 10784000 | 5392000 | 5392000
[5 empty] | 0 |  | 0
2 | Global Drug Facility | 2.1 Application Review and Monitoring | 1219200 | 184450 | 1403650 | 1091000 | 2494650 | 1247325 | 1247325
| (GDF) | 2.2 Supply | 582400 | 139500 | 721900 | 66727000 | 67448900 | 26979560 | 40469340
|  | 2.3 Drug Management | 102400 | 6200 | 108600 | 105000 | 213600 | 106800 | 106800
|  | 2.4 General Management and Support | 822400 | 117800 | 940200 | 532000 | 1472200 | 736100 | 736100
|  | Sub-total | 2726400 | 447950 | 3174350 | 68455000 | 71629350 | 29069785 | 42559565
[5 empty] | 0 |  | 0
3 | General Management and Administration | 3.1 Resource Mobilization and Financial Management | 496000 | 144150 | 640150 | 170000 | 810150 | 405075 | 405075
| (GMA) | 3.2 Information Management | 339200 | 34100 | 373300 | 210000 | 583300 | 291650 | 291650
|  | 3.3 General Administration | 262400 | 162750 | 425150 | 140000 | 565150 | 282575 | 282575
|  | Sub-total | 1097600 | 341000 | 1438600 | 520000 | 1958600 | 979300 | 979300
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
|  | TOTAL | 6208000 | 1284950 | 7492950 | 76879000 | 84371950 | 35441085 | 48930865

## 02-03 VS 04-05
| A P P R O V E D |  | TOTAL | P R O P O S E D |  | TOTAL
| 2002 | 2003 | 2002-2003 | 2004 | 2005 | 2004-2005
Support and Innovations
Governance | 826170 | 1335886 | 2162056 | 771800 | 771800 | 1543600
Coordination and Growth (Partnerships) | 824975 | 467820 | 1292795 | 1405675 | 1405675 | 2811350
Working Groups | 230960 | 105203 | 336163 | 741000 | 741000 | 1482000
Communications and Advocacy | 1897365 | 1511262 | 3408627 | 2473525 | 2473525 | 4947050
Sub-total | 3779470 | 3420171 | 7199641 | 5392000 | 5392000 | 10784000
Global Drug Facility
Application Review and Monitoring | 468500 | 564774 | 1033274 | 1247325 | 1247325 | 2494650
Supply | 23400800 | 41386927 | 64787727 | 26979560 | 40469340 | 67448900
Drug Management | 109330 | 202722 | 312052 | 106800 | 106800 | 213600
General Management and Support | 1174590 | 342164 | 1516754 | 736100 | 736100 | 1472200
Sub-total | 25153220 | 42496587 | 67649807 | 29069785 | 42559565 | 71629350
General Management and Administration
Resource Mobilization and Financial Management | 774000 | 174811 | 948811 | 405075 | 405075 | 810150
Information Management | 263200 | 499008 | 762208 | 291650 | 291650 | 583300
General Administration | 565000 | 437310 | 1002310 | 282575 | 282575 | 565150
Sub-total | 1602200 | 1111129 | 2713329 | 979300 | 979300 | 1958600
|  |  |  | 0 | 0
TOTAL WORKPLAN COST | 30534890 | 47027887 | 77562777 | 35441085 | 48930865 | 84371950
Notes:
(1) For 2003 drug supply, 50% (approximately 20M) of the budget was expected to be through GDF and 50% will be direct procurement supported from funds from national sources, GFATM and donors
(2) For 2004-2005 drug supply, 40% of the funding for the expected 5 million patient treatments will be required by the end of 2003 and 60% or the remaining of the estimated patient treatment will be required by the end of 2004.